## Sheet1
Task Mode | 任务名称 | Duration | Start | Finish | Predecessors | Resource Names
Manually Scheduled | 需求分析 | 7 days | Thu 9/1/11 | Fri 9/9/11 |  | yanbing
Auto Scheduled | UI Design | 2 days? | Thu 9/1/11 | Fri 9/2/11 |  | yanbing
Auto Scheduled | DataBase Design | 2 days? | Mon 9/5/11 | Tue 9/6/11 | 2 | yanbing
Auto Scheduled | Interface Design | 2 days? | Wed 9/7/11 | Thu 9/8/11 | 3 | yanbing
Manually Scheduled | MainFrameWork Design | 1 day? | Fri 9/9/11 | Fri 9/9/11 | 4 | yanbing
Manually Scheduled | 开发 | 38 days | Mon 9/12/11 | Mon 10/31/11 | 5 | yanbing
Auto Scheduled | eChart Server Content | 14 days | Tue 9/13/11 | Fri 9/30/11 |  | yanbing
Auto Scheduled | eChart Server Content | 1 day | Sat 10/8/11 | Sat 10/8/11 |  | yanbing
Manually Scheduled | eChart Client | 10 days | Sun 10/9/11 | Thu 10/20/11
Auto Scheduled | eChart Server Login & Setting | 2 days? | Fri 10/21/11 | Mon 10/24/11 | 5 | yanbing
Manually Scheduled | eChart Server Monitor&Optimize | 2 days | Tue 10/25/11 | Wed 10/26/11 | 7 | yanbing
Manually Scheduled | 整合&测试&发布 | 3 days | Thu 10/27/11 | Mon 10/31/11 |  | yanbing